## Overview
Doubts
Instruments & materials
Data type
All water samples (filtered) are to be analysed for:
- Total metolachlor, MESA and MOXA concentrations
- Concentration of 4 metolachlor stereoisomers
- Isotope signature of each stereoisomer
All filtered residues are to be analysed for:
- Fraction of organic content
- Sorbed metolachlor, MESA and MOXA concentrations
- Sorbed metolachlor for 4 stereoisomer
All soil composites are analysed for:
- Moisture content & pH
- Liquid and sorbed concentrations of meto, MESA and MOXA
- Isotope signature and stereoisomer fractions in liquid phase
- Soil organic content (foc)
- Granulometric data
Core profile samples (1-2m depth), start and end at each transect (Total cores = x6)
- Soil organic content
- Moisture content, pH
- Redox potential (Eh)
- Profile of pesticide analytics as for soil composites
Note: number of cores per transect could depend on difficulty/invasiveness on field.
| Time Line | 2016
|  | February |  |  |  | Mars |  |  |  | Avril |  |  |  | Mai |  |  |  |  | June |  |  |  | July |  |  |  | Aug |  |  |  |  | Sept |  |  |  | Oct
| Week of Monday the: | 2016-02-09 00:29 | 2016-02-16 00:29 | 2016-02-23 00:29 | 2016-03-01 00:29 | 2016-03-08 00:29 | 2016-03-15 00:29 | 2016-03-22 00:29 | 2016-03-29 00:29 | 2016-04-05 00:29 | 2016-04-12 00:29 | 2016-04-19 00:29 | 2016-04-26 00:29 | 2016-05-03 00:29 | 2016-05-10 00:29 | 2016-05-17 00:29 | 2016-05-24 00:29 | 2016-05-31 00:29 | 2016-06-07 00:29 | 2016-06-14 00:29 | 2016-06-21 00:29 | 2016-06-28 00:29 | 2016-07-05 00:29 | 2016-07-12 00:29 | 2016-07-19 00:29 | 2016-07-26 00:29 | 2016-08-02 00:29 | 2016-08-09 00:29 | 2016-08-16 00:29 | 2016-08-23 00:29 | 2016-08-30 00:29 | 2016-09-06 00:29 | 2016-09-13 00:29 | 2016-09-20 00:29 | 2016-09-27 00:29 | 2016-10-04 00:29 | 2016-10-11 00:29 | 2016-10-18 00:29 | 2016-10-25 00:29 | 2016-11-01 00:29
Field | Punctual Tasks / To do before the campaign | bar: 2016-02-09 00:29 to 2016-04-05 00:29
a | S-metolachlor application rates and locations are obtained from survey to the farmer | 2016-02-09 00:29: Create map with Sylvain; 2016-03-22 00:29: check!
b | Grab sampling at drainage outlet during event -> Not further discussed | 2016-03-08 00:29: check!
c | Hanna instrument (Ponsel, Caudan, France) | bar: 2016-02-16 00:29
d | Test Doppler flowmeter (2150 Isco) is functioning - Benoit (March 2th) | 2016-03-01 00:29: check!; 2016-03-15 00:29: check!
Test Refrigerated automatic sampler is functioning - Benoit (March 2th) | bar: 2016-03-01 00:29
| Test Pluviometre et modification du protocole du pluviomètre, voir avec Benoît et Sylvain (March 4th) | 2016-03-01 00:29: check!; 2016-03-15 00:29: check!
Prévoir bon de commande/voir s’il y en a ? cadenas/chaîne etc. + Réservation voiture (2 mars matin) | bar: 2016-02-23 00:29
Acheter/cadenas/chaîne (3-4 mars matin) | bar: 2016-03-01 00:29
Préparation/renforcement de la cabane (7, 9 mars après-midi) | bar: 2016-03-01 00:29 to 2016-03-08 00:29
Door construction in the lab (8 Mars) | bar: 2016-03-08 00:29
Search rotational device for automatic sampler (7 Mars, Apre-midi) | bar: 2016-03-01 00:29 to 2016-03-08 00:29
g | Installation on field (Eric, Benoit, Sarah, Pablo (10th March)… including: | bar: 2016-02-23 00:29; 2016-03-08 00:29
- Pluviometre (raingauge) (9-10th march) | bar: 2016-03-08 00:29
- Curage sur 2 m (sortie buse) (9 mars) | bar: 2016-03-08 00:29
| - Probe/sonde | 2016-03-08 00:29: check!; 2016-03-15 00:29: check!
- Refrigerated auntomatic sampler, with carousel (note: define frequency of collection) | bar: 2016-03-08 00:29
| - Batteries | 2016-03-08 00:29: check!; 2016-03-15 00:29: check!
- Doppler flow meter | bar: 2016-03-08 00:29
| - Orpheus mini, tipping bucket | 2016-03-08 00:29: check!; 2016-03-15 00:29: check!
| - Thermocouple / Thermometers | 2016-03-08 00:29: check!; 2016-03-15 00:29: check!
| Positionnement des jalons des transepts (17 mars) | 2016-03-15 00:29: check!
| Calibrage et mise en place par technicien Ponsel (17 mars) | 2016-03-15 00:29: check!
| Test du matériel sur le terrain (17 mars) | 2016-03-15 00:29: check!
| Formation de Pablo et Sarah au matériel de terrain (17 mars) - Benoit, Eric, Sarah and Pablo | 2016-03-15 00:29: check!
i | Buy thermometer -> Gwenael suggests: 'one thermocouple' | 2016-02-16 00:29: Benoit; 2016-02-23 00:29: check!
j | Buy and install 3 'sondes' (20 and 40 cm, 1x per transect) | bar: 2016-02-09 00:29
k | Define sampling frequency for automatic sampler (based on Marie's Data) - Pablo | 2016-03-01 00:29: check!; 2016-03-15 00:29: check!
l | Define grab sampling volumes needed - Pablo, check with Charline | 2016-03-01 00:29: check!; 2016-03-15 00:29: check!
m | Car reservation for the season - Pablo | Registration sent to: Charline MARTIN | Contact: Monsieur Blumentritt Hervé | x | [5 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | [5 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check!
Planning Milestone #1 (See Planning Word.docx) - Due date March 11. | bar: 2016-03-01 00:29
Preparation Meeting - March 11, 14h00, Send Doodle to All for confirmation (Pablo) | bar: 2016-02-23 00:29; 2016-03-08 00:29
| Pablo and Sahra are trained to collected data on the field and trouble-shooting (Benoît) - Due date March 26. | 2016-03-22 00:29: check!
| Field material and devices are tested on the site (Benoît, Eric) - Due date March 17 (changed from 26th) | 2016-03-15 00:29: check!
| Field protocols are validated. Soil collection locations on the catchments are known (Sahra, Pablo) | 2016-03-22 00:29: check!
| Include detailed sampling: 50cm colum (@3 depths = 3cm, 20cm, 50cm) representative soil sampling at 5x transect (at 4 times : startCamp., Directly after application, endCamp.). 1 applications. Sample potentials: 72-192 | 2016-03-22 00:29: check!
| Final checking, last trouble shooting, preparation of field and the lab for sample collection (All) | 2016-03-29 00:29: check!
| Coordination with the Rouffach team (Charline) - see checklist for potential conflicts | 2016-03-29 00:29: check!
No. | Weekly Field Tasks - WATER | bar: 2016-02-09 00:29 to 2016-04-05 00:29
1 | Conductivity, pH, dissolved oxygen and redox potential is measured at the catchment outlet using Hanna Instrument Probe (Sonde). | [8 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | [5 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check!
2 | Discharge measured at the catchment outlet using a Doppler flowmeter (2150 Isco). | [8 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | [5 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check!
3 | Flow-proportional samples are taken (to be determined based on the 2012 data) with a refrigerated automatic sampler (Isco Avalanche) - carousel equiped with 24 bottles of 1L each. | [8 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | [5 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check!
4 | Weekly grab water samples are collected from the drain outlet (2 L = 2 flasks). Discharge is also calculated during sampling with chronometer (pesticide load apprximation). | [8 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | [5 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check!
No. | Weekly Field Tasks - SOIL & FILTERED PARTICLES | bar: 2016-02-09 00:29 to 2016-04-05 00:29
5 | Bulk integrative soil samples are collected weekly along 3 longitudinal transects (see Map 1), ONLY on the maize and sugar beet plots (map with culture plots to be provided). | [8 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | [5 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check!
5a | a) 3 composite topsoil samples (0 to 3 cm) are collected along the transects (each Y m, systematic sampling protocol to be determined on the maize and sugar beet plots) before the herbicide application and then weekly. | [8 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | [5 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check!
5b | b) Detailed soil sampling (5 separated composite samples for each transect) is carried out immediately after S-metolachlor application (but application may not occur simultaneously), 50 days after application, and 100 days (mid-june) after application | [8 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | [5 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check!
| Other Hydro Measurements - Questions / doubts | 2016-02-09 00:29: Answers:
6 | Local rain gauges (measure our margin of uncertainty/spatial variability ~ station is 7km away) | 2016-02-09 00:29: One rain gauge will be installed.
7 | Evaporation Pans (confirm actual evaporation calculations) | 2016-02-09 00:29: Discussed with Sylvain. Evaporation records are more reliable from METEO France. Therefore, no need for cross check.
Things to Remember!! Methods
| Water samples are stored in the dark at 4 °C after each runoff event and placed on ice during transportation to the laboratory for chemical analysis (within 24 hs following the sample collection). | [8 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | [5 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check!
| The soil samples are kept frozen at -20 °C until pesticide analysis. | [8 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | [5 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check!
REF | Weekly instrument checkup (report: after field visit) | bar: 2016-02-09 00:29 to 2016-04-05 00:29
1 | Hanna sonde functioning report - Sarah/Pablo | [8 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | [5 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check!
2 | Doppler flowmeter (2150 Isco) functioning report - Sarah/Pablo | [8 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | [5 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check!
2 | Refrigerated automatic sampler functioning report - Sarah/Pablo | [8 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | check! | [5 empty] | check! | check! | check! | check! | check! | check! | check! | check! | check! | check!
3 | Computer (software? Downloading the data? Etc.? How are 2 and 3 connected? The same?)
REF | Weekly material checklist (prep: Monday) | bar: 2016-02-09 00:29 to 2016-04-05 00:29
3 | 10L glass Schott bottle (permanently in outlet station?)
4 | XXL glass bottle for weekly grab sample
5a | Plastic bags for bulk soil samples (size? Number = 3)
5b | Plastic bags for bulk soil samples (size? Number = 5)
Lab | Punctual Tasks | bar: 2016-02-09 00:29 to 2016-04-05 00:29
Lab | Ongoing Tasks | bar: 2016-02-09 00:29 to 2016-04-05 00:29
1 | 2 to 10 L (to be determined) water samples are filtered (0.45 µm, to be confirmed), extracted by solid-phase extraction (SPE), concentrated under nitrogen flux to 1 droplet, and resuspended in 500 µL ACN. S-metolachlor, MESA and MOXA are quantified with a GC-MS/MS and LC-MS/MS system according to Charline’s/Benoît’s protocols.
2 | Analysis of filter, OC of suspended solids, XRD, geochemical composition?
3 | S-metolachlor, MESA and MOXA are extracted, concentrated and purified from soil samples based on Charline s’/Benoît’s protocol.
4 | S-metolachlor enantiomer analysis is carried out with a Trace GC 2000 series GC-MS apparatus (Thermo Fisher Scientific, Waltham, MA, USA) equipped with 30 m × 0.25 mm ID, 0.25 µm film 20% tert-butyldimethylsilyl-β-cyclodextrin dissolved in 15% phenyl-, 85% methylpolysiloxane chiral column (BGB Analytik, Boeckten, Switzerland) as previously described (Elsayed et al., 2015).
5 | C and N isotope ratios are measured in triplicates with a GC-C-IRMS continuous-flow system (Delta V plus); ESIA of S-metolachlor is carried with a 30 m × 0.25 mm ID, 0.25 µm film 20% tert-butyldimethylsilyl-β-cyclodextrin dissolved in 15% phenyl-, 85% methylpolysiloxane chiral column (BGB Analytik, Boeckten, Switzerland).
Data to review:
Coring (2m depths per transect) - data is available from phytoret
Tarriere.. X1 (10cm)
Note on B15: While composite samples save cost and time, they limit or ability to eventually apply stochastic evaluations of our concepts and models. Understanding the variability of key parameters (e.g. Ks, OC, moisture content, temperature) would provide us with the ability to state what is the range of uncertainty in our model predictions. Examples of data gathered in different studies: Loll and Moldrup (2000) collected for two agricultural field plots (100m x 50 m): Site A) Four parameters (f, p_b, Ks, soil-water retention) at 24 points, at least at 3 depths (10, 30, 50 cm) and 4 at additional four depths. = 88 values per parameter. Site B) Four parameters ("") etc., at 5 depths = 120 values per parameter.
Note on B19: Ghafoor et al., 2011 Degradation of pesticides in soils is both spatially variable and also one of the most sensitive factors determining losses to surface water and groundwater. To date, no general guidance is available on suitable approaches for dealing with spatial variation in pesticide degradation in catchment or regional scale modeling applications. The purpose of the study was to study the influence of various soil physical, chemical and microbiological characteristics on pesticide persistence in a small (13 km2) agricultural catchment. Degradation rate constants are highly variable with coefficients of variation ranging between 42 and 64% for herbicides. Soil pH and the proportion of active microorganisms (r) together explained 69% of the variation; Freundlich sorption co-efficient (Kf) explained 88% of variation in degradation rate; soil pH was sgnificant predictor (pb0.05) for persistence. Loll and Moldrup (2000) provide a multiplicative adjustment to T1/2 (see p. 967), not considered by Dairon. Loll and Moldrup (2000) find that predicting pesticide mass fraction leached would be seriously underestimated if spatial variability of organic carbon content was not considered. foc appears to be a key parameter regulating sorption, thus tracking its spatio-temporal variability should be a valuable constraint (especially if moisture and temp do not turn out to be sufficiently rigid constraints).
Note on B25: Boesten and van der Linden (1991) applied an empirical dependency relationship between degradation (half-life) and depth (See: Loll and Moldrop 2000), which we ignore. Understanding what are the likely degradation pathways / electron acceptors and knowing what is the change in Eh along the soil column we can justify leaving this dependency out of the model. However, we need to demonstrate that the Eh beyond a certain depth is below the expected TEAPs resp. for metolachlor degradation.
Note on B35: Checked with Charline -> this is the Sonde that we will use to record: pH, Eh, Temp & DO
Note on B44: pablo alvarez: Reservation is made for the 16th, early morning. The TRAFIC BLEU is not available the nightbefore. Check with Benoit is the Jumper (9 - Blessig) is OK as well?
Note on B67: Marie found that: metolachlor leached up to a 1 m depth on July 10 with concentrations of 4 × 10-3 mg kg-1dry.

## AvantPartir
LISTE DU MATERIEL A AMENER:
Date:
Prélèvements (weekly):
- sachets PE (pour 500g de sol chacun environ)
- cuillère en fer propre
- stylo/marqueur
- pissette d'éthanol
- pissette d'eau distillée
- essuie-tout (paper towels)
Prélèvements (Detailed) - above plus:
- Tarriere
Note: Mettre tout cela dans un seau (night before)
- glacière avec pains de glace (cooler with ice)
- flaconnage propre avec bouchon
- étiquettes
Données:
- ordinateur chargé
- batteries de rechange chargées
- câbles (pour récupérer les données)
- 2 batteries chargées pour le préleveur
- thermocouple (w batteries)
Autres:
- solution d'étalonnage pour la sonde (calibration solution)
- membranes O2 dissous pour éventuel remplacement
- clefs cabane
- appareil photo
- équipement de sécurité (chaussures, gants, lunettes, etc..)
- matériel de base (stylos, parafilm, poubelles, essuie-tout, etc…)
- rondelles + level ruler (if pluvio needs adjustment)

## AuTerrain
Liste des tâches à ne pas oublier:
Date:
- prélèvement sols
- prélèvement eau (outlet)
- prélèvement eau (drain grab sample)
- changement flaconnage préleveur
- données préleveur
- données débitmètre
- données sonde multiparamètre
- données pluviomètre
- nettoyage sonde débitmètre si nécessaire
- changement batteries
- relancer préleveur
- refermer cabane
Observations:
(pas de données, étalonnage sonde, photos, etc…)

## LabellingTerrain
312
Sarah defends!
[9 empty] | 11-12mai | 13-16mai
|  | W0 | W1 | W2 | W3 | W3B | W4 | W5 | W6 | W6B | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | [5 empty] | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Water | Echant # [mL] | 2016-03-29 00:29 | 2016-04-05 00:29 | 2016-04-12 00:29 | 2016-04-19 00:29 | 2016-04-21 | 2016-04-26 00:29 | 2016-05-03 00:29 | 2016-05-10 00:29 | 2016-05-13 | 2016-05-17 00:29 | 2016-05-24 00:29 | 2016-05-31 00:29 | 2016-06-07 00:29 | 2016-06-14 00:29 | 2016-06-21 00:29 | 2016-06-28 00:29 | 2016-07-05 00:29 | 2016-07-12 00:29 | 2016-07-19 00:29 | 2016-07-26 00:29 | 2016-08-02 00:29 | 2016-08-09 00:29 | 2016-08-16 00:29 | 2016-08-23 00:29 | 2016-08-30 00:29 | 2016-09-06 00:29 | 2016-09-13 00:29 | 2016-09-20 00:29 | 2016-09-27 00:29 | 2016-10-04 00:29 | 2016-10-11 00:29 | 2016-10-18 00:29 | 2016-10-25 00:29 | 2016-11-01 00:29
Alteckendorf Outlet - Filtered Water | AO-1- | AO-1-W0 | AO-1-W1 | AO-1-W2 | AO-1-W3 | AO-1-W3B | AO-1-W4 | AO-1-W5 | AO-1-W6 | AO-1-W6B | AO-1-W7 | AO-1-W8 | AO-1-W9 | AO-1-W10 | AO-1-W11 | AO-1-W12 | AO-1-W13 | AO-1-W14 | AO-1-W15 | AO-1-W16 | x | x | x | x | x | [10 empty] | 1
| AO-2- | AO-2-W0 | AO-2-W1 | AO-2-W2 | AO-2-W3 | AO-2-W3B | AO-2-W4 | AO-2-W5 | AO-2-W6 | AO-2-W6B | AO-2-W7 | AO-2-W8 | AO-2-W9 | AO-2-W10 | AO-2-W11 | AO-2-W12 | AO-2-W13 | AO-2-W14 | AO-2-W15 | AO-2-W16 | x | x | x | x | x | [10 empty] | 2
| AO-3- | AO-3-W0 | AO-3-W1 | AO-3-W2 | AO-3-W3 | AO-3-W3B |  | AO-3-W5 | AO-3-W6 | AO-3-W6B | AO-3-W7 | AO-3-W8 | AO-3-W9 | AO-3-W10 | AO-3-W11 | AO-3-W12 | AO-3-W13 | AO-3-W14 | AO-3-W15 | AO-3-W16 | x | x | x | x | x | [10 empty] | 3
| AO-4- |  | AO-4-W1 | AO-4-W2 | AO-4-W3 | AO-4-W3B |  | AO-4-W5 | AO-4-W6 | AO-4-W6B |  | AO-4-W8 | AO-4-W9 | AO-4-W10 | AO-4-W11 | AO-4-W12 | AO-4-W13 | AO-4-W14 | AO-4-W15 | AO-4-W16 | x | x | x | x | x | [10 empty] | 4
| AO-5- |  | AO-5-W1 | AO-5-W2 | AO-5-W3 | AO-5-W3B |  | AO-5-W5 | AO-5-W6 | AO-5-W6B |  | AO-5-W8 | AO-5-W9 | AO-5-W10 | AO-5-W11 | AO-5-W12 | AO-5-W13 | AO-5-W14 | AO-5-W15 | AO-5-W16 | x | x | x | x | x | [10 empty] | 5
| AO-6- | 2016-04-05 00:29: AO-6-W1; 2016-04-12 00:29: AO-6-W2; 2016-04-19 00:29: AO-6-W3; 2016-05-03 00:29: AO-6-W5; 2016-05-13: AO-6-W6B; 2016-05-24 00:29: AO-6-W8; 2016-05-31 00:29: AO-6-W9; 2016-06-07 00:29: AO-6-W10; 2016-06-14 00:29: AO-6-W11; 2016-06-21 00:29: AO-6-W12; 2016-06-28 00:29: AO-6-W13; 2016-07-05 00:29: AO-6-W14; 2016-07-12 00:29: AO-6-W15; 2016-07-19 00:29: AO-6-W16; 2016-07-26 00:29: x; 2016-08-02 00:29: x; 2016-08-09 00:29: x; 2016-08-16 00:29: x; 2016-08-23 00:29: x | 6
| AO-7- | 2016-04-05 00:29: AO-7-W1; 2016-04-12 00:29: AO-7-W2; 2016-04-19 00:29: AO-7-W3; 2016-05-03 00:29: AO-7-W5; 2016-05-13: AO-7-W6B; 2016-05-24 00:29: AO-7-W8; 2016-05-31 00:29: AO-7-W9; 2016-06-07 00:29: AO-7-W10; 2016-06-14 00:29: AO-7-W11; 2016-06-21 00:29: AO-7-W12; 2016-06-28 00:29: AO-7-W13; 2016-07-05 00:29: AO-7-W14; 2016-07-12 00:29: AO-7-W15; 2016-07-19 00:29: AO-7-W16; 2016-07-26 00:29: x; 2016-08-02 00:29: x; 2016-08-09 00:29: x; 2016-08-16 00:29: x; 2016-08-23 00:29: x | 7
| AO-8- | 2016-04-05 00:29: AO-8-W1; 2016-04-12 00:29: AO-8-W2; 2016-04-19 00:29: AO-8-W3; 2016-05-03 00:29: AO-8-W5; 2016-05-13: AO-8-W6B
| AO-9- | 2016-04-05 00:29: AO-9-W1; 2016-04-12 00:29: AO-9-W2; 2016-04-19 00:29: AO-9-W3; 2016-05-03 00:29: AO-9-W5; 2016-05-13: AO-9-W6B
| AO-10- | 2016-04-05 00:29: AO-10-W1; 2016-04-12 00:29: AO-10-W2; 2016-04-19 00:29: AO-10-W3; 2016-05-03 00:29: AO-10-W5; 2016-05-13: AO-10-W6B
| AO-11- | 2016-04-05 00:29: AO-11-W1; 2016-04-12 00:29: AO-11-W2; 2016-04-19 00:29: AO-11-W3; 2016-05-03 00:29: AO-11-W5; 2016-05-13: AO-11-W6B
| AO-12- | 2016-04-05 00:29: AO-12-W1; 2016-04-12 00:29: AO-12-W2; 2016-04-19 00:29: AO-12-W3; 2016-05-13: AO-12-W6B
| Water Samples | 2016-03-29 00:29: 3; 2016-04-05 00:29: 2; 2016-04-12 00:29: 12; 2016-04-19 00:29: 12; 2016-04-21: 5; 2016-04-26 00:29: 2; 2016-05-03 00:29: 11; 2016-05-10 00:29: 5; 2016-05-13: 12; 2016-05-17 00:29: 3; 2016-05-24 00:29: 7; 2016-05-31 00:29: 7; 2016-06-07 00:29: 7; 2016-06-14 00:29: 7; 2016-06-21 00:29: 7; 2016-06-28 00:29: 7; 2016-07-05 00:29: 7; 2016-07-12 00:29: 7; 2016-07-19 00:29: 7
Pesti. Filters | Flask # | 2016-03-29 00:29 | 2016-04-05 00:29 | 2016-04-12 00:29 | 2016-04-19 00:29 | 2016-04-26 00:29 | 2016-05-03 00:29 | 2016-05-10 00:29 | 2016-05-13 | 2016-05-17 00:29 | 2016-05-24 00:29 | 2016-05-31 00:29 | 2016-06-07 00:29 | 2016-06-14 00:29 | 2016-06-21 00:29 | 2016-06-28 00:29 | 2016-07-05 00:29 | 2016-07-12 00:29 | 2016-07-19 00:29 | 2016-07-26 00:29 | 2016-08-02 00:29 | 2016-08-09 00:29 | 2016-08-16 00:29 | 2016-08-23 00:29 | 2016-08-30 00:29 | 2016-09-06 00:29 | 2016-09-13 00:29 | 2016-09-20 00:29 | 2016-09-27 00:29 | 2016-10-04 00:29 | 2016-10-11 00:29 | 2016-10-18 00:29 | 2016-10-25 00:29 | 2016-11-01 00:29
Alteckendorf Outlet - Filters Pesticides - FP | AFP-1- | 2016-03-29 00:29: AFP-1-W0 (a,b,c); 2016-04-05 00:29: AFP-1-W1 (a,b,c,d); 2016-07-19 00:29: x; 2016-07-26 00:29: x; 2016-08-02 00:29: x; 2016-08-09 00:29: x; 2016-08-16 00:29: x; 2016-11-01 00:29: 1
| a | 2016-03-29 00:29: 100mL/F
| b | 2016-03-29 00:29: 2x 50mL/F
| c | 2016-03-29 00:29: 36mL/F
| AFP-2- | 2016-03-29 00:29: AFP-2-W0 (a,b); 2016-07-19 00:29: x; 2016-07-26 00:29: x; 2016-08-02 00:29: x; 2016-08-09 00:29: x; 2016-08-16 00:29: x; 2016-11-01 00:29: 2
| a | 2016-03-29 00:29: 2x 50mL/F
| b | 2016-03-29 00:29: 2x 50mL
| AFP-3- | 2016-03-29 00:29: AFP-3-W0; 2016-07-19 00:29: x; 2016-07-26 00:29: x; 2016-08-02 00:29: x; 2016-08-09 00:29: x; 2016-08-16 00:29: x; 2016-11-01 00:29: 3
| a | 2016-03-29 00:29: 50mL/F
| AFP-4- | 2016-07-19 00:29: x; 2016-07-26 00:29: x; 2016-08-02 00:29: x; 2016-08-09 00:29: x; 2016-08-16 00:29: x; 2016-11-01 00:29: 4
| AFP-5- | 2016-07-19 00:29: x; 2016-07-26 00:29: x; 2016-08-02 00:29: x; 2016-08-09 00:29: x; 2016-08-16 00:29: x; 2016-11-01 00:29: 5
| AFP-6- | 2016-07-19 00:29: x; 2016-07-26 00:29: x; 2016-08-02 00:29: x; 2016-08-09 00:29: x; 2016-08-16 00:29: x; 2016-11-01 00:29: 6
AFP-7-
AFP-8-
AFP-9-
AFP-10-
AFP-11-
AFP-12-
Pesti. Filters | Flask # | 2016-03-29 00:29 | 2016-04-05 00:29 | 2016-04-12 00:29 | 2016-04-19 00:29 | 2016-04-26 00:29 | 2016-05-03 00:29 | 2016-05-10 00:29 | 2016-05-13 | 2016-05-17 00:29 | 2016-05-24 00:29 | 2016-05-31 00:29 | 2016-06-07 00:29 | 2016-06-14 00:29 | 2016-06-21 00:29 | 2016-06-28 00:29 | 2016-07-05 00:29 | 2016-07-12 00:29 | 2016-07-19 00:29 | 2016-07-26 00:29 | 2016-08-02 00:29 | 2016-08-09 00:29 | 2016-08-16 00:29 | 2016-08-23 00:29 | 2016-08-30 00:29 | 2016-09-06 00:29 | 2016-09-13 00:29 | 2016-09-20 00:29 | 2016-09-27 00:29 | 2016-10-04 00:29 | 2016-10-11 00:29 | 2016-10-18 00:29 | 2016-10-25 00:29 | 2016-11-01 00:29
Alteckendorf Outlet - Filters MES (Suspended Solids - SS) | AFSS-1- | 2016-03-29 00:29: AFSS-1-W0; 2016-07-19 00:29: x; 2016-07-26 00:29: x; 2016-08-02 00:29: x; 2016-08-09 00:29: x; 2016-08-16 00:29: x; 2016-11-01 00:29: 1
| a | 2016-03-29 00:29: 60mL/F
| AFSS-2- | 2016-03-29 00:29: AFSS-2-W0; 2016-07-19 00:29: x; 2016-07-26 00:29: x; 2016-08-02 00:29: x; 2016-08-09 00:29: x; 2016-08-16 00:29: x; 2016-11-01 00:29: 2
| a | 2016-03-29 00:29: 50mL/F
| AFSS-3- | 2016-03-29 00:29: AFSS-3-W0; 2016-07-19 00:29: x; 2016-07-26 00:29: x; 2016-08-02 00:29: x; 2016-08-09 00:29: x; 2016-08-16 00:29: x; 2016-11-01 00:29: 3
| a | 2016-03-29 00:29: 50mL/F
| AFSS-4- | 2016-07-19 00:29: x; 2016-07-26 00:29: x; 2016-08-02 00:29: x; 2016-08-09 00:29: x; 2016-08-16 00:29: x; 2016-11-01 00:29: 4
| AFSS-5- | 2016-07-19 00:29: x; 2016-07-26 00:29: x; 2016-08-02 00:29: x; 2016-08-09 00:29: x; 2016-08-16 00:29: x; 2016-11-01 00:29: 5
| AFSS-6- | 2016-07-19 00:29: x; 2016-07-26 00:29: x; 2016-08-02 00:29: x; 2016-08-09 00:29: x; 2016-08-16 00:29: x; 2016-11-01 00:29: 6
AFSS-7-
AFSS-8-
AFSS-9-
AFSS-10-
AFSS-11-
AFSS-12-
[34 empty] | 0 | Water samples
[34 empty] | 0 | Water samples
[34 empty] | #REF! | Filtered samples
|  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Soil (weekly) | Bag # & Date | 2016-03-29 00:29 | 2016-04-05 00:29 | 2016-04-12 00:29 | 2016-04-19 00:29 | 2016-04-26 00:29 | 2016-05-03 00:29 | 2016-05-10 00:29 | 2016-05-17 00:29 | 2016-05-24 00:29 | 2016-05-31 00:29 | 2016-06-07 00:29 | 2016-06-14 00:29 | 2016-06-21 00:29 | 2016-06-28 00:29 | 2016-07-05 00:29 | 2016-07-12 00:29 | 2016-07-19 00:29 | 2016-09-08 | 2016-07-26 00:29 | 2016-08-02 00:29 | 2016-08-09 00:29 | 2016-08-16 00:29 | 2016-08-23 00:29 | 2016-08-30 00:29 | 2016-09-06 00:29 | 2016-09-13 00:29 | 2016-09-20 00:29 | 2016-09-27 00:29 | 2016-10-04 00:29 | 2016-10-11 00:29 | 2016-10-18 00:29 | 2016-10-25 00:29 | 2016-11-01 00:29
Plateau Nord | AW-N- |  | AW-N-1 | AW-N-2 | AW-N-3 | AW-N-4 | AW-N-5 | AW-N-6 | AW-N-7 | AW-N-8 | AW-N-9 | AW-N-10 | AW-N-11 | AW-N-12 | AW-N-13 | AW-N-14 | AW-N-15 |  | AW-N-16 | x | x | x | x | x | [10 empty] | 1
Talweg | AW-T- |  | AW-T-1 | AW-T-2 | AW-T-3 | AW-T-4 | AW-T-5 | AW-T-6 | AW-T-7 | AW-T-8 | AW-T-9 | AW-T-10 | AW-T-11 | AW-T-12 | AW-T-13 | AW-T-14 | AW-T-15 |  | AW-T-16 | x | x | x | x | x | [10 empty] | 2
Plateau Sud | AW-S- |  | AW-S-1 | AW-S-2 | AW-S-3 | AW-S-4 | AW-S-5 | AW-S-6 | AW-S-7 | AW-S-8 | AW-S-9 | AW-S-10 | AW-S-11 | AW-S-12 | AW-S-13 | AW-S-14 | AW-S-15 |  | AW-S-16 | x | x | x | x | x | [10 empty] | 3
A: Alteck; W: weekly; Transect: (N,T,S); Weeknumber: (1-30) | Weekly Samples | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3 | [15 empty] | #VALUE! | Soil samples
[35 empty] | #REF! | Soil samples
DayApp. | D0 | D1 | AW-N-1 AW-T-1 AW-S-1: D50; AW-N-2 AW-T-2 AW-S-2: D100
Code | -I- | -II- | AW-N-1 AW-T-1 AW-S-1: -III-; AW-N-2 AW-T-2 AW-S-2: -IV-
Aplication Date | Plots
2016-03-20 | No. 34 (#N2), 45 (#T9) & 40 (#S11) | 9 | 16 | 23 | 30 | 37 | 44 | 53 | 60 | 67 | 74 | 81 | 88 | 95 | 102 | 109 | 116 |  | 172
2016-04-13 | Most | 0 | 0 | 1 | 8 | 15 | 22 | 29 | 36 | 43 | 50 | 57 | 64 | 71 | 78 | 85 | 92 |  | 148
2016-04-27 | Dutt: No. 3 & 5 | 0 | 0 | 0 | 0 | 0 | 7 | 14 | 21 | 28 | 35 | 42 | 49 | 56 | 63 | 70 | 77 |  | 133
Waiting for Speich & Schmitt - Maize | No. 1, & 10
| (Planned not actual) | 2017-03-29 | 2017-04-05 | 2017-04-12 | 2017-04-19 | 2017-04-26 | 2017-05-03 | 2017-05-10 | 2017-05-17 | 2017-05-24 | 2017-05-31 | 2017-06-07 | 2017-06-14 | 2017-06-21 | 2017-06-28 | 2017-07-05 | 2017-07-12 | 2017-07-19 | 2017-07-26
|  | W0 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 |  | W16
Transect & Depth | PlotNo-Depth | 2016-03-29 00:29 | 2016-04-05 00:29 | 2016-04-14 | 2016-04-19 00:29 | 2016-04-26 00:29 | 2016-05-03 00:29 | 2016-05-12 | 2016-05-17 00:29 | 2016-05-24 00:29 | 2016-05-31 00:29 | 2016-06-07 00:29 | 2016-06-14 00:29 | 2016-06-21 00:29 | 2016-06-28 00:29 | 2016-07-05 00:29 | 2016-07-12 00:29 | 2016-07-19 00:29 | 2016-09-08 | [14 empty] | Old PlotCodes
Nord (Depth 3cm) | 1-D3 | 2016-03-29 00:29: N-I-1-D3; 2016-04-19 00:29: ->; 2016-04-26 00:29: ->; 2016-05-03 00:29: ->; 2016-05-12: ->; 2016-07-12 00:29: N-IV-1-D3 | [6 empty] | x | x | x | N -35-D3
| 2-D3 | 2016-03-29 00:29: N-I-2-D3; 2016-05-12: N-III; 2016-06-28 00:29: N-IV-2-D3 | [11 empty] | N -34-D3
| 3-D3 | 2016-03-29 00:29: N-I-3-D3; 2016-04-19 00:29: ->; 2016-04-26 00:29: ->; 2016-05-03 00:29: ->; 2016-05-12: ->; 2016-05-17 00:29: N-II; 2016-06-14 00:29: N-III-3-D3; 2016-07-12 00:29: N-IV-3-D3 | [11 empty] | N -33-D3
| 4-D3 | 2016-03-29 00:29: N-I-4-D3; 2016-04-14: N-II; 2016-05-31 00:29: N-III; 2016-07-12 00:29: N-IV-4-D3 | [11 empty] | N -42-D3
| 5-D3 | N-I-5-D3 |  |  | -> | -> | -> | -> | N-II | -> | -> | -> | N-III-5-D3 |  |  |  | N-IV-5-D3 | [13 empty] | N -23-D3
| 6-D3 | 2016-03-29 00:29: N-I-6-D3; 2016-04-14: N-II; 2016-05-31 00:29: N-III; 2016-07-12 00:29: N-IV-7-D3 | [11 empty] | N -22-D3 Est
| 7-D3 | 2016-03-29 00:29: N-I-7-D3; 2016-04-14: N-II; 2016-07-12 00:29: N-IV-7-D3 | [11 empty] | N- 22 Ouest New!
| 8-D3 | 2016-03-29 00:29: N-I-8-D3; 2016-04-14: N-II; 2016-05-31 00:29: N-III; 2016-07-12 00:29: N-IV-8-D3 | [11 empty] | N -21-D3
Nord (Depth 20cm) | 1-D20 | 2016-03-29 00:29: N-I-1-D20; 2016-04-19 00:29: ->; 2016-04-26 00:29: ->; 2016-05-03 00:29: ->; 2016-05-12: ->; 2016-05-31 00:29: ->; 2016-07-12 00:29: N-IV-1-D20 | [9 empty] | N -35-D20
| 2-D20 | 2016-03-29 00:29: N-I-2-D20; 2016-05-12: N-III; 2016-06-28 00:29: N-IV-2-D20 | [11 empty] | N -34-D20
| 3-D20 | 2016-03-29 00:29: N-I-3-D20; 2016-04-19 00:29: ->; 2016-04-26 00:29: ->; 2016-05-03 00:29: ->; 2016-05-12: ->; 2016-05-17 00:29: N-II; 2016-06-14 00:29: N-III-3-D20; 2016-07-12 00:29: N-IV-3-D20 | [11 empty] | N -33-D20
| 4-D20 | 2016-03-29 00:29: N-I-4-D20; 2016-04-14: N-II; 2016-05-31 00:29: N-III; 2016-07-12 00:29: N-IV-4-D20 | [11 empty] | N -42-D20
| 5-D20 | N-I-5-D20 |  |  | -> | -> | -> | -> | N-II | -> | -> | -> | N-III-5-D20 |  |  |  | N-IV-5-D20 | [13 empty] | N -23-D20
| 6-D20 | 2016-03-29 00:29: N-I-6-D20; 2016-04-14: N-II; 2016-05-31 00:29: N-III; 2016-07-12 00:29: N-IV-7-D20 | [11 empty] | N -22-D20 Est
| 7-D20 | 2016-03-29 00:29: N-I-7-D20; 2016-04-14: N-II; 2016-07-12 00:29: N-IV-7-D20 | [11 empty] | N - 22 - D20 Ouest New!
| 8-D20 | 2016-03-29 00:29: N-I-8-D20; 2016-04-14: N-II; 2016-05-31 00:29: N-III; 2016-07-12 00:29: N-IV-8-D20 | [11 empty] | N -21-D20
Talweg (Depth 3cm) | 9-D3 | 2016-03-29 00:29: T-I- 9-D3; 2016-05-12: T-III; 2016-06-28 00:29: T-IV- 9-D3 | [11 empty] | T -45-D3
| 10-D3 | 2016-03-29 00:29: T-I-10-D3; 2016-04-19 00:29: ->; 2016-04-26 00:29: ->; 2016-05-03 00:29: ->; 2016-05-12: ->; 2016-05-31 00:29: ->; 2016-07-12 00:29: T-IV-10-D3 | [9 empty] | T -25-D3
| 4-D3 | 2016-03-29 00:29: T-I-4-D3; 2016-04-14: T-II; 2016-05-31 00:29: T-III; 2016-07-12 00:29: T-IV-4-D3 | [11 empty] | T -42-D3
| 5-D3 | 2016-03-29 00:29: T-I-5-D3; 2016-04-19 00:29: ->; 2016-04-26 00:29: ->; 2016-05-03 00:29: ->; 2016-05-12: ->; 2016-05-17 00:29: T-II; 2016-06-14 00:29: T-III-5-D3; 2016-07-12 00:29: T-IV-5-D3 | [11 empty] | T -23-D3
| 6-D3 | 2016-03-29 00:29: T-I-6-D3; 2016-04-14: T-II; 2016-05-31 00:29: T-III; 2016-07-12 00:29: T-IV-7-D3 | [11 empty] | T -22-D3 Est
| 7-D3 | 2016-03-29 00:29: T-I-7-D3; 2016-04-14: T-II; 2016-05-31 00:29: T-III; 2016-07-12 00:29: T-IV-7-D3 | [11 empty] | T- 22 -D3 Ouest New!
| 8-D3 | 2016-03-29 00:29: T-I-8-D3; 2016-04-14: T-II; 2016-05-31 00:29: T-III; 2016-07-12 00:29: T-IV-8-D3 | [11 empty] | T -21-D3
Talweg (Depth 20cm) | 9-D20 | 2016-03-29 00:29: T-I- 9-D20; 2016-05-12: T-III; 2016-06-21 00:29: T-X-9-D3; 2016-06-28 00:29: T-IV- 9-D20 | [11 empty] | T -45-D20
| 10-D20 | 2016-03-29 00:29: T-I-10-D20; 2016-04-19 00:29: ->; 2016-04-26 00:29: ->; 2016-05-03 00:29: ->; 2016-05-12: ->; 2016-05-31 00:29: ->; 2016-06-21 00:29: T-X-10-D3; 2016-07-12 00:29: T-IV-10-D20 | [9 empty] | T -25-D20
| 4-D20 | 2016-03-29 00:29: T-I-4-D20; 2016-04-14: T-II; 2016-05-31 00:29: T-III; 2016-07-12 00:29: T-IV-4-D20 | [11 empty] | T -42-D20
| 5-D20 | T-I-5-D20 |  |  | -> | -> | -> | -> | T-II | -> | -> | -> | T-III-5-D20 |  |  |  | T-IV-5-D20 | [13 empty] | T -23-D20
| 6-D20 | 2016-03-29 00:29: T-I-6-D20; 2016-04-14: T-II; 2016-05-31 00:29: T-III; 2016-07-12 00:29: T-IV-7-D20 | [11 empty] | T -22-D20 Est
| 7-D20 | 2016-03-29 00:29: T-I-7-D20; 2016-04-14: T-II; 2016-07-12 00:29: T-IV-7-D20 | [11 empty] | T-22-D20 Ouest New!
| 8-D20 | 2016-03-29 00:29: T-I-8-D20; 2016-04-14: T-II; 2016-05-31 00:29: T-III; 2016-07-12 00:29: T-IV-8-D20 | [11 empty] | -21-D3
Sud (Depth 3cm) | 11-D3 | 2016-03-29 00:29: S-I- 11-D3; 2016-05-12: S-III; 2016-06-28 00:29: S-IV- 11-D3 | [11 empty] | -40-D3
| 12-D3 | 2016-03-29 00:29: S-I- 12-D3; 2016-04-14: S-II; 2016-05-31 00:29: S-III; 2016-07-12 00:29: S-IV- 12-D3 | [11 empty] | -8-D3
| 13-D3 | 2016-03-29 00:29: S-I- 13-D3; 2016-04-14: S-II; 2016-05-31 00:29: S-III; 2016-07-12 00:29: S-IV- 13-D3 | [11 empty] | -9-D3
Sud (Depth 20cm) | 11-D20 | 2016-03-29 00:29: S-I- 11-D20; 2016-05-12: S-III; 2016-06-28 00:29: S-IV- 11-D20 | [11 empty] | -40-D20
| 12-D20 | 2016-03-29 00:29: S-I- 12-D20; 2016-04-14: S-II; 2016-05-31 00:29: S-III; 2016-07-12 00:29: S-IV- 12-D20 | [11 empty] | -8-D20
| 13-D20 | 2016-03-29 00:29: S-I- 13-D20; 2016-04-14: S-II; 2016-05-31 00:29: S-III; 2016-07-12 00:29: S-IV- 13-D20 | [11 empty] | -9-D20
| Detailed Samples | 36 | 0 | 20 | 10 | 10 | 10 | 16 | 8 | 4 | 23 | 3 | 6 | 2 | 9 | 2 | 31
| Detailed D3 only | 18 | 0 | 10 | 5 | 5 | 5 | 8 | 4 | 2 | 11.5 | 1.5 | 3 | 1 | 4.5 | 1 | 15.5
| D20 | 18 | 0 | 10 | 5 | 5 | 5 | 8 | 4 | 2 | 11.5 | 1.5 | 3 | 1 | 4.5 | 1 | 15.5
| Weekly + D3 | 18 | 3 | 13 | 8 | 8 | 8 | 11 | 7 | 5 | 14.5 | 4.5 | 6 | 4 | 7.5 | 4 | 18.5
| Total Soil Samples | 36 | 3 | 23 | 13 | 13 | 13 | 19 | 11 | 7 | 26 | 6 | 9 | 5 | 12 | 5 | 34
Note on C9: pablo alvarez: Collected on 30-Mars-2016
Note on E84: pablo alvarez: Detailed moved to Thursday the 14th.

## LabLoad_Plan
| Week No. | W0 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
Water | Num Samples | 3 | 2 | 12 | 12 | 2 | 11 | 5 | 3 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
Days (of 7hrs) to complete full analysis: | Filter | 0.5 | 0.33333 | 2 | 2 | 0.33333 | 1.8333 | 0.83333 | 0.5 | 1.1667 | 1.1667 | 1.1667 | 1.1667 | 1.1667 | 1.1667 | 1.1667 | 1.1667 | 1.1667
| MO & MES | 0.375 | 0.25 | 1.5 | 1.5 | 0.25 | 1.375 | 0.625 | 0.375 | 0.875 | 0.875 | 0.875 | 0.875 | 0.875 | 0.875 | 0.875 | 0.875 | 0.875
| Filter-SPE | 0.46154 | 0.30769 | 1.8462 | 1.8462 | 0.30769 | 1.6923 | 0.76923 | 0.46154 | 1.0769 | 1.0769 | 1.0769 | 1.0769 | 1.0769 | 1.0769 | 1.0769 | 1.0769 | 1.0769
| Sorbed-Conc. | 0.15 | 0.1 | 0.6 | 0.6 | 0.1 | 0.55 | 0.25 | 0.15 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35
| Water-SPE | 0.33333 | 0.22222 | 1.3333 | 1.3333 | 0.22222 | 1.2222 | 0.55556 | 0.33333 | 0.77778 | 0.77778 | 0.77778 | 0.77778 | 0.77778 | 0.77778 | 0.77778 | 0.77778 | 0.77778
| Pest-Conc. & δ | 0.13043 | 0.086957 | 0.52174 | 0.52174 | 0.086957 | 0.47826 | 0.21739 | 0.13043 | 0.30435 | 0.30435 | 0.30435 | 0.30435 | 0.30435 | 0.30435 | 0.30435 | 0.30435 | 0.30435
| Total Days | 1.9503 | 1.3002 | 7.8012 | 7.8012 | 1.3002 | 7.1511 | 3.2505 | 1.9503 | 4.5507 | 4.5507 | 4.5507 | 4.5507 | 4.5507 | 4.5507 | 4.5507 | 4.5507 | 4.5507
| Week No. | W0 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
Soil | D3 + Weekly | 18 | 3 | 13 | 8 | 8 | 8 | 11 | 7 | 5 | 14.5 | 4.5 | 6 | 4 | 7.5 | 4 | #REF! | 18.5
| D20 | 18 | 0 | 10 | 5 | 5 | 5 | 8 | 4 | 2 | 11.5 | 1.5 | 3 | 1 | 4.5 | 1 | #REF! | 15.5
Days (of 7hrs) to complete full analysis: | Sieve | 3 | 0.25 | 1.0833 | 0.66667 | 0.66667 | 0.66667 | 0.91667 | 0.58333 | 0.41667 | 1.2083 | 0.375 | 0.5 | 0.33333 | 0.625 | 0.33333 | #REF! | 1.5417
| Moisture | 1.5 | 0.25 | 1.0833 | 0.66667 | 0.66667 | 0.66667 | 0.91667 | 0.58333 | 0.41667 | 1.2083 | 0.375 | 0.5 | 0.33333 | 0.625 | 0.33333 | #REF! | 1.5417
| Organic Carbon | 2.25 | 0.375 | 1.625 | 1 | 1 | 1 | 1.375 | 0.875 | 0.625 | 1.8125 | 0.5625 | 0.75 | 0.5 | 0.9375 | 0.5 | #REF! | 2.3125
| pH | 1 | 0.16667 | 0.72222 | 0.44444 | 0.44444 | 0.44444 | 0.61111 | 0.38889 | 0.27778 | 0.80556 | 0.25 | 0.33333 | 0.22222 | 0.41667 | 0.22222 | #REF! | 1.0278
| Extraction | 2.7692 | 0.46154 | 2 | 1.2308 | 1.2308 | 1.2308 | 1.6923 | 1.0769 | 0.76923 | 2.2308 | 0.69231 | 0.92308 | 0.61538 | 1.1538 | 0.61538 | #REF! | 2.8462
| Pest-Conc. & δ | 0.9 | 0.15 | 0.65 | 0.4 | 0.4 | 0.4 | 0.55 | 0.35 | 0.25 | 0.725 | 0.225 | 0.3 | 0.2 | 0.375 | 0.2 | #REF! | 0.925
| Total (D3+Weekly) | 11.4192 | 1.6532 | 7.1639 | 4.4085 | 4.4085 | 4.4085 | 6.0618 | 3.8575 | 2.7553 | 7.9905 | 2.4798 | 3.3064 | 2.2043 | 4.133 | 2.2043 | #REF! | 10.1948
| Total (D20) | 11.4192 |  | 7.1639 | [6 empty] | 7.9905
| Load From: | W0-W4 | W5-W9 | W10-W13 | W14-W16
| Person Days Needed: | 60.6258 | 54.5175 | 30.3264 | #REF!
|  | Avril | Mai | Juin | Juilliet
| 1 | 59.6258 |  | 107.9697 | #REF!
| 2 |  | 95.1433 | 106.9697
| 3 |  | 94.6433 | 105.9697
| 4 | 58.6258 | 93.6433 |  | #REF!
| 5 | 58.1258 |  |  | #REF!
| 6 | 57.1258 | 92.6433 | 104.9697
| 7 | 56.1258 |  | 104.4697
| 8 | 55.1258 |  | 103.4697
| 9 |  | 91.6433 | 102.4697
| 10 |  | 91.1433 | 101.4697
| 11 | 54.1258 | 90.1433
| 12 | 53.6258 | 89.1433
| 13 | 52.6258 | 88.1433 | 100.4697
| 14 | 51.6258 |  | 99.9697
| 15 | 50.6258 |  | 98.9697
| 16 |  |  | 97.9697
| 17 |  | 87.6433 | 96.9697
| 18 | 49.6258 | 86.6433
| 19 | 49.1258 | 85.6433
| 20 | 48.1258 | 84.6433 | 95.9697
| 21 | 47.1258 |  | 95.4697
| 22 | 46.1258 |  | 94.4697
| 23 |  | 83.6433 | 93.4697
| 24 |  | 83.1433 | 92.4697
| 25 | 45.1258 | 82.1433
| 26 | 44.6258 | 81.1433
| 27 | 43.6258 | 80.1433 | 91.4697
| 28 | 42.6258 |  | 90.9697
| 29 | 41.6258 |  | 89.9697
| 30 |  | 79.1433 | 88.9697
| 31 |  | 78.6433

## Weekly Transect
Grams per Spoon | 9
Spoons per sample point | 5
Code Transect | Plot's Width [m] | [7 empty] | Total
Farmer | Kopp | Kopp | Kopp | Dutt | Kopp | Dutt | Friess | Speich
AW-N- | 98 | 41 | 33 | 42 | 47 | 130 | 173.5 | 60.1 | 624.6
Distance % of Transect | 15.69% | 6.564% | 5.283% | 6.724% | 7.525% | 20.81% | 27.78% | 9.622% | 100%
Sampling Centers | 4.707 | 1.9693 | 1.585 | 2.0173 | 2.2574 | 6.244 | 8.3333 | 2.8866 | 30 |  | Scale | Grams | Spoons
Distance [m] btw points | 17.1719 | 18 |  | 14 | 15 | 20 | 21 | 15 | 1350
Distance to neighbours' boundary | (13m) | (9m) |  | (13m) | (16m) | (15m) | (12m) | (15m) | Composite Mass [g]
Code Transect | Plot's Width [m] | [6 empty] | Total |  | 5 - 10% | 40 | 13.3333
Farmer | Kopp | Kopp | Kopp | Dutt | Kopp | Schmitt | Friess
AW-T- | 96.5 | 45 | 28.6 | 43.8 | 35.8 | 117 | 135.8 | 502.5 |  | 10 - 15% | 60 | 20
Distance % of Transect | 19.2% | 8.955% | 5.692% | 8.716% | 7.124% | 23.28% | 27.02% | 100% |  | 15 - 20% | 80 | 26.6667
Sampling Centers | 5.3771 | 2 | 1.5936 | 2.4406 | 1.9948 | 6 | 6 | 25 |  | 25 - 30% | 120 | 40
Distance [m] btw points | 16 | 20 |  | 15 | 12 | 17 | 20 | 1125 |  | 20 - 25% | 100 | 33.3333
Distance to neighbours' boundary | (15m) | (7m) |  | (14m) | (-) | (15m) | (15m) | Composite Mass [g]
[10 empty] | 30 - 35% | 140 | 46.6667
[11 empty] | 35 - 40% | 160 | 53.3333
[11 empty] | 40 - 45% | 180 | 60
Code Transect | Plot's Width [m] |  |  | Total
AW-S- | 86.2 | 179.8 | 218 | 484
Distance % of Transect | 17.81% | 37.15% | 45.04% | 100%
Sampling Centers | 4.6306 | 9.6587 | 11.7107 | 26
Distance [m] btw points | 15 | 18 | 17 | 1170
Distance to neighbours' boundary | (13m) | (7m) | (21m) | Composite Mass [g]

## Detailed Transect
|  | total g | 230 |  | Area %
|  | points | 5 |  | 0 - 10% | 4
|  | spoons/point | 5 |  | 10 - 20% | 5
[5 empty] | 20 - 30% | 6
|  | g/spoon | 9.2 |  | 30 - 40% | 7
|  | Need | 22 spoons |  | 40 - 50% | 8
| Grams per Spoon | 9 |  | Min. Grams | Spoons | Points
| Spoons per sample point | 5 |  | 160 | 17.7778 | 4
| Code Transect |  |  |  |  | Plot's Width [m] |  |  |  | Total
| A-N-(I,II,III,IV)-Plot#-D3/D20 | 98 | 41 | 33 | 42 | 47 | 130 | 173.5 | 60.1 | 624.6
| Distance % of Transect | 15.69% | 6.564% | 5.283% | 6.724% | 7.525% | 20.81% | 27.78% | 9.622% | 100%
| Sampling Centers | 5 | 4 | 4 | 4 | 4 | 6 | 6 | 4 | 37
| Distance [m] btw points | 18.4 | 8.75 | 6.75 | 9 | 10.25 | 20.6667 | 27.9167 | 13.525
| Distance to neighbours' boundary | (11m) | (7m) | Measure directly | (7m) | (7m) | (16m) | (17m) | (9m)
Revised Parcels | Code Transect |  |  |  |  | Plot's Width [m] |  |  |  | Total
Kopp 2 = 1 | A-N-(I,II,III,IV)-Plot#-D3/D20 | 98 | 74 |  | 42 | 47 | 130 | 173.5 | 60.1 | 624.6
| Distance % of Transect | 15.69% | 11.85% |  | 6.724% | 7.525% | 20.81% | 27.78% | 9.622% | 100%
| Sampling Centers | 5 | 5 |  | 4 | 4 | 6 | 6 | 4 | 34
| Distance [m] btw points | 18.4 | 13 |  | 9 | 10.25 | 20.6667 | 27.9167 | 13.525
| Distance to neighbours' boundary | (11m) | (10.5m) |  | (7m) | (7m) | (16m) | (17m) | (9m)
| Code Transect |  |  |  |  | Plot's Width [m] |  |  | Total
| A-T-(I,II,III,IV)-(Plot#)-D3/D20 | 96.5 | 45 | 28.6 | 43.8 | 35.8 | 117 | 135.8 | 502.5
| Distance % of Transect | 19.2% | 8.955% | 5.692% | 8.716% | 7.124% | 23.28% | 27.02% | 100%
| Sampling Centers | 5 | 4 | 4 | 4 | 4 | 6 | 6 | 33
| Distance [m] btw points | 18.1 | 9.75 | 5.65 | 9.45 | 7.45 | 18.5 | 21.6333
| Distance to neighbours' boundary | (11m) | (7m) | Measure directly | (7.5m) | Measure directly | (12m) | (14m)
Revised Parcels | Code Transect |  |  |  |  | Plot's Width [m] |  |  | Total
Kopp 2 = 1 | A-T-(I,II,III,IV)-(Plot#)-D3/D20 | 96.5 | 73.6 |  | 43.8 | 35.8 | 117 | 135.8 | 502.5
| Distance % of Transect | 19.2% | 14.65% |  | 8.716% | 7.124% | 23.28% | 27.02% | 100%
| Sampling Centers | 5 | 5 |  | 4 | 4 | 6 | 6 | 30
| Distance [m] btw points | 18.1 | 13 |  | 9.45 | 7.45 | 18.5 | 21.6333
| Distance to neighbours' boundary | (11m) | (10.5m) |  | (7.5m) | Measure directly | (12m) | (14m)
| Code Transect |  | Plot's Width [m] |  | Total
| A-S-(I,II,III,IV)-(Plot#)-D3/D20 | 86.2 | 179.8 | 218 | 484
| Distance % of Transect | 17.81% | 37.15% | 45.04% | 100%
| Sampling Centers | 5 | 7 | 8 | 20
| Distance [m] btw points | 16.04 | 24.8286 | 26.5
| Distance to neighbours' boundary | (9m) | (14m) | (14m)

## LitReview
|  | Loll and Muldrop 2000 | Lindahl et al., 2005 | Sheikh et al., 2009 | Sheikh | Ghafoor et al., 2011
STUDY AREA | Catchment (ha) | NA | 900 |  |  | 1300
| Field/Plot (ha) | 0.5 | 30 |  |  | NA
| Field relative elevation (measured points) | NA | 77 points |  |  | NA
SOIL | Catchment soils size distribution + OC (values) | NA | 93
| Top soil (< 25cm) |  | 51
| Subsoil (25 & 75cm) |  | 24
| Deep soil (100cm) |  | 18
| Catchment soil water retention (soil cylinder: 7x5cm) | NA | 4
| Catchment Ksat (soil cylinder: 7x5cm) | NA | 4
| Field soils size distribution + OC (values) | 24 | 127 |  |  | 80
| Top soil (< 25cm) | Only first 10cm (190cm3 samples / location), used Humus x 0.58 ≈ OC | 77 |  |  | 16 locations (5 samples per location) analyzed detailed: textures, pH and OC (+N, +K, +P)
| Subsoil (25 & 75cm) |  | 25 |  |  | No samples below 20cm
| Deep soil (100cm) |  | 25
| Field soil water retention, bulk density | 120 | 3
| 10cm | 24 | Only top soil (20 cm) at the three key positions of the study. (with soil column replicates)
| 30cm | 24
| 50cm | 24
| 70cm | 24
| 90cm | 24
| Field Ksat (across depth) | 120 | 3
| 10cm | 24 | "Near-saturated" Ksat measured with tension infiltrometer - i.e. only top soil
| 30cm | 24
| 50cm | 24
| 70cm | 24
| 90cm | 24
| Field dispersivity & tracer (soil columns 20cm x 20 cm) | NA | 3
HYDROLOGY | Piezometric pressure (values/yr) |  | 117
| Low-valley, midslope & hilltop |  | 3
| Depths measured |  | 2
| Measures per year |  | 13
| Years measured |  | 7
| Drain discharge (field outlet) |  | Continuous
| Grab samples (13 peak events/month) |  | 13
| Study OBJECTIVE | Interesting findings from soil sampling
Loll and Muldrop 2000
Lindahl et al., 2005 | Identify key controls on herbicide (MCPA) leaching at field and catchment scales. Losses compared to measured concentrations in drainflow from a single field for 1 year, and in catchment stream outlet for 7 years. | Soil properties dependent on topography. Hilltops: highest clay content, lower OC and higher bulk density Midslopes: depleted of clay (erosion) Hollows: Highest organic carbon, lower bulk density, higher saturated water content.
Ghafoor et al., 2011 | Not a modelling study. The purpose was to study the influence of various soil physical, chemical and microbiological characteristics on pesticide persistence in contrasting cultivated soils in a small (13 km2) agricultural catchment. Found bioavailability and sorption parameters explain most variability in degradation patterns. (AKind to Dairon) | If we obtain evolution of SOC, sorption parameters (allowing us to fit a Freundlich - K_f): we could check against a regression model for the valididty of these parameters at explaining degradation extent. The same could be said about moisture and temperature.
Other studies to check out:
Foussereau, X., W. D. Graham, and P.S.C. Rao, Stochastic analysis of Transient Flow in Unsaturated Heterogeneous Soils, Water Resources Research, 26(4), 891-910, 2000.
Note on C5: 2 field plots each at: (100mx50m)
Note on C18: At each depth 100cm3 "undisturbed" samples taken.
Note on C24: At each depth 100cm3 "undisturbed" samples taken.
Note on D30: One soil colum replicate per location (hillslope, slopes and hollows).

## Contacts
Dernière mise à jour |  | 2016-03-30
Nom prénom | Occupation du sol - 2016 | Confirmation oc. Sol | Tel | Portable | Mail | Accord transect | Etat des discussions | Récupération produits | Enquête envoi | Enquête reçue | Herbicide prévu | Herbicide appliqué | Date d'application | Dose | Lieu achat | A été contacté le: | On a laisse un message
Speich Nicolas | Blé (Nord ouest) et non défni parcelle triangulaire au centre | terrain | 03 88 21 90 76 (fils) 03.69.26.51.93 (père) | A obtenir | A obtenir | oui |  | non | non | non | Dual Gold | à préciser | non appliquée | ? | à préciser |  | 04/04/2016, 11/04/16, 02/05/16, 18/05,02/06,08/06
Kopp Michel | Betterave sur toutes les parcelles | téléphone | 03 88 51 50 16 (sa mère) | 06 75 06 87 07 | A obtenir | oui |  | oui | non | non | Mercantor Gold | Mercantor Gold et "Menir", Isard | 2016-04-13 | Echantillon à analyser, 0,6L/ha | à préciser |  | 04/04/2016, 11/04/16, 02/05/16,02/06
Burger | Betterave sur l'unique parcelle | téléphone | 03 88 51 57 10 | 06 68 93 93 77 | burger.eric67@gmail.com | oui |  | oui | non | non | à préciser | Mercantor Gold | 2016-04-14 | Echantillon (pur+cuve) à analyser | à préciser |  | 2016-04-04
Dutt Rémi | Maïs (Blé : rien a été dit) | terrain | 03 88 51 61 80 (sa mère) 03 88 51 56 87 | 06 89 84 13 09 | A obtenir | oui |  | oui | non | non | Maïs: Callisto avec Casper ; Isard | Isard | 2016-04-27 | 1,1L/ha | à préciser | 2016-04-04 | 2016-05-02
Mr Mattis (hors commune), donc lien Alteckendorf Alfred Scholler (beau-frère) | Blé ou maïs --> Betteraves | terrain | 03 88 51 61 98 | A obtenir | A obtenir | oui |  | non | non | non | à préciser | à préciser | ? | ? | à préciser | 2016-04-11 | 2016-04-04
Mr Freiss | Betterave sur les 3 parcelles | téléphone | 03 88 70 57 40 | 06 09 03 33 12 | remy.friess-66url@orange.fr | oui |  | non | non | non | Mercantor | à préciser | 2016-03-20 | 0,6L/ha | à préciser | 2016-06-08 | Na
Mme Schmitt Monique (Sœur) - Marlyse (travaille sur la parcelle, donc point contact) | Maïs | téléphone | 03 88 51 51 40 | 06 09 90 62 96 (Mari Marlise) | A obtenir | oui |  | non | non | non | Dual Gold/Casper/Rattrapage/Elumis | Dual Gold/Casper/Epissard | 2016-05-25 | Dual Gold: 1,2 L/ha; Casper: 50g/ha; 3L/ha: Epissard | Comptoir Hochfelden | 04/04/2016, 09/05/16 | 2016-05-02
Mr Staath Pascal | Blé | téléphone | 03 88 51 63 90 | 06 85 92 78 21 | A obtenir | oui |  | non | non | non | Atlantis WG, Canopia | NA | 2016-04-11 | NA | NA | 2016-04-11 | Aucune repondeur
Comptoir agricole d'Hochfelden
4 route de Strasbourg Hochfelden
03 88 89 09 28
Récupération des itinéraires techniques

## Hydrograms
Week 1
Week 2
Week 3
Week 4
Week 5

## Preleveur
Re-launch the sampling program :
- Click on "stop programme".
- Change Batteries
Conduct two tests before relaunching the program:
1st: Test Moving the arm to flask no 1.
Go to "manual" options/tasks -> choose: "Actioner le bras" -> Move to "Flacon 1" + enter -> You will now hear the arm movving.
2nd: Test the batteries
Still in "manual" options/tasks -> choose "echantillon manuel" -> pump 110mL of water into flacon #1 -> Wait for the pumping to be over and check that the amount is approx. correct. (1/3 of the flask)
If no problems with the batteries move on to the final action. Else, try to adjust the clamps on the batteries so that there is full contact. If problems persist, call Benoit: 03 68 85 05 02
3rd: Finally, ensure the arm is still over flacon 1. If not, repeat the first test.
Lancer le programme
- Follow the procedure by validating each time the pre-set option (normally it is already set so there is nothing to change).
(Note: one step will be "action continue?". Do not change this. The answer is "Non", we do not want the arm to keep rotating after finishing the 12 bottles.)
- Continue to monitor the procedure and at the end of it, choose "lancer le programme"

## other notes
GPS Points Taken at Talweg, where the inclination from the north transect tapers down.
48.7888 | 7.584
48 47 19,56 N | 7 35 2,27 E